## Sheet1
TASKS | ASSIGNED TO | REASON
START OF INSPECTION JOB | MAN | SAFE TASK
GAS CHECK[TANK] | ROBOT | UNSAFE TASK
REPORT STATUS OF [GAS CHECK] TO HUMAN | ROBOT | AS IN DATABASE
HUMAN GIVES AFFIRMATIVE REPLY | MAN | SAFE TASK
CHECK TANK ISOLATION [STEAM LINES, PRODUCT LINES, ELECTRICAL POWER] | ROBOT | UNSAFE LOCATION
CHECK INSPECTION AREA FOR [FALLING OBJECTS HAZARDS] | ROBOT | UNSAFE LOCATION
CHECK INSPECTION AREA FOR [SLIPPING HAZARDS] | ROBOT | AS IN DATABASE
INSPECT STRUCTURAL WELDS [ACCESS WAYS AND CLIPS] | MAN | SAFE LOCATION
REVIEW CATHODIC POTENTIAL READINGS | MAN | SAFE TASK
INSPECT APPURTENANCES [LOWER TANK AREA] | MAN | SAFE LOCATION
INSPECT APPURTENANCES [UPPER TANK AREA] | ROBOT | AS IN DATABASE
INSPECT APPURTENANCES [TANK ROOF] | ROBOT | AS IN DATABASE
MEASURE THE TANK HEIGHT [FROM TOP TO BOTTOM] | ROBOT | AS IN DATABASE
REPORT MEASUREMENT TO HUMAN | ROBOT | AS IN DATABASE
EXTERNAL SURFACE PREPARATION [TANK OUTER SHELL PLATE] | MAN | SAFE LOCATION
EXTERNAL VISUAL INSPECTION [TANK OUTER SHELL PLATE] | MAN | SAFE LOCATION
EXTERNAL VISUAL INSPECTION [TANK BOTTOM TO FOUNDATION] | ROBOT | AS IN DATABASE
EXTERNAL ULTRASONIC THICKNESS TESTING [TANK OUTER SHELL PLATE] | MAN | SAFE LOCATION
CLIMB UNTO [TANK ROOF] | ROBOT | UNSAFE TASK
EXTERNAL SURFACE PREPARATION [TANK ROOF] | ROBOT | AS IN DATABASE
EXTERNAL VISUAL INSPECTION[TANK ROOF] | ROBOT | AS IN DATABASE
CLIMB INTO [TANK INTERIOR ROOF] | ROBOT | UNSAFE TASK
INTERNAL VISUAL INSPECTION[TANK INTERIOR ROOF PLATES] | ROBOT | UNSAFE TASK
INTERNAL ULTRASONIC THICKNESS TESTING[TANK ROOF THIN AREA] | ROBOT | UNSAFE TASK
PENETRANT TESTING [IF TANK INTERIOR IS PADDED], SKIP [IF TANK INTERIOR ROOF IS NOT PADDED] | ROBOT | UNSAFE TASK
SPARK TESTING [IF RECOATING OF TANK INTERIOR ROOF IS PLANNED], [IF RECOATING OF TANK INTERIOR IS NOT PLANNED SKIP] | ROBOT | UNSAFE TASK
MOVE TO [TANK INTERIOR SHELL PLATES] | ROBOT | AS IN DATABASE
INTERNAL VISUAL INSPECTION[TANK INTERIOR SHELL PLATES] | ROBOT | UNSAFE TASK
MOVE TO [TANK INTERIOR BOTTOM] | ROBOT | AS IN DATABASE
INTERNAL VISUAL INSPECTION [TANK INTERIOR BOTTOM] | ROBOT | UNSAFE TASK
INTERNAL HAMMER TESTING[TANK INTERIOR BOTTOM] | ROBOT | UNSAFE TASK
INTERNAL ULTRASONIC THICKNESS TESTING[TANK INTERIOR BOTTOM] | ROBOT | UNSAFE TASK
INTERNAL VISUAL INSPECTION[TANK INTERIOR SHELL TO BOTTOM WELD] | ROBOT | UNSAFE TASK
INTERNAL VACCUUM TESTING [TANK INTERIOR BOTTOM LAP WELDS] | ROBOT | UNSAFE TASK
CLIMB OUT OF [TANK INTERIOR] TO [TANK EXTERIOR] | ROBOT | UNSAFE TASK
INSPECTION RESULT GENERATION | ROBOT | AS IN DATABASE
UPLOAD INSPECTION RESULT | ROBOT | AS IN DATABASE
GO THROUGH THE INSPECTION RESULT | MAN | AS IN DATABASE
AUTHORIZE THE INSPECTION RESULT | MAN | AS IN DATABASE
END OF INSPECTION JOB | ROBOT | OTHERS(UNKNOWN)