## Sheet1
LISTS OF TASK FOR API 653 ABOVEGROUND TANK INSPECTION JOB
SEQUENCE NO | TASK NAME
1 | START OF INSPECTION JOB
2 | GAS CHECK[TANK]
3 | REPORT STATUS OF [GAS CHECK] TO HUMAN
4 | HUMAN GIVES AFFIRMATIVE REPLY
5 | CHECK TANK ISOLATION [STEAM LINES, PRODUCT LINES, ELECTRICAL POWER]
6 | CHECK INSPECTION AREA FOR [FALLING OBJECTS HAZARDS]
7 | CHECK INSPECTION AREA FOR [SLIPPING HAZARDS]
8 | INSPECT STRUCTURAL WELDS [ACCESS WAYS AND CLIPS]
9 | REVIEW CATHODIC POTENTIAL READINGS
10 | INSPECT APPURTENANCES [LOWER TANK AREA]
11 | INSPECT APPURTENANCES [UPPER TANK AREA]
12 | INSPECT APPURTENANCES [TANK ROOF]
13 | MEASURE THE TANK HEIGHT [FROM TOP TO BOTTOM]
14 | REPORT MEASUREMENT TO HUMAN
15 | EXTERNAL SURFACE PREPARATION [TANK OUTER SHELL PLATE]
16 | EXTERNAL VISUAL INSPECTION [TANK OUTER SHELL PLATE]
17 | EXTERNAL VISUAL INSPECTION [TANK BOTTOM TO FOUNDATION]
18 | EXTERNAL ULTRASONIC THICKNESS TESTING [TANK OUTER SHELL PLATE]
19 | CLIMB UNTO [TANK ROOF]
20 | EXTERNAL SURFACE PREPARATION [TANK ROOF]
21 | EXTERNAL VISUAL INSPECTION[TANK ROOF]
22 | CLIMB INTO [TANK INTERIOR ROOF]
23 | INTERNAL VISUAL INSPECTION[TANK INTERIOR ROOF PLATES]
24 | INTERNAL ULTRASONIC THICKNESS TESTING[TANK ROOF THIN AREA]
25 | PENETRANT TESTING [IF TANK INTERIOR IS PADDED], SKIP [IF TANK INTERIOR ROOF IS NOT PADDED]
26 | SPARK TESTING [IF RECOATING OF TANK INTERIOR ROOF IS PLANNED], [IF RECOATING OF TANK INTERIOR IS NOT PLANNED SKIP]
27 | MOVE TO [TANK INTERIOR SHELL PLATES]
28 | INTERNAL VISUAL INSPECTION[TANK INTERIOR SHELL PLATES]
29 | MOVE TO [TANK INTERIOR BOTTOM]
30 | INTERNAL VISUAL INSPECTION [TANK INTERIOR BOTTOM]
31 | INTERNAL HAMMER TESTING[TANK INTERIOR BOTTOM]
32 | INTERNAL ULTRASONIC THICKNESS TESTING[TANK INTERIOR BOTTOM]
33 | INTERNAL VISUAL INSPECTION[TANK INTERIOR SHELL TO BOTTOM WELD]
34 | INTERNAL VACCUUM TESTING [TANK INTERIOR BOTTOM LAP WELDS]
35 | CLIMB OUT OF [TANK INTERIOR] TO [TANK EXTERIOR]
36 | INSPECTION RESULT GENERATION
37 | UPLOAD INSPECTION RESULT
38 | GO THROUGH THE INSPECTION RESULT
39 | AUTHORIZE THE INSPECTION RESULT
40 | END OF INSPECTION JOB